Construction Sector Transparency Initiative-Ethiopia (CoST-Ethiopia)

Assurance Report on Reactive Disclosed Project and Contract Information of Assosa University Phase Four Dormitory Building Constructions

November 2018

Addis Ababa, Ethiopia

Contents

List of Tables	iii

Acronyms/ Abbreviations	iv

1.	Executive Summary	1

2.	Introduction	7

2.1.	Objectives of the Assignment	8

3.	Disclosed of Project  Information	10

3.1.	Project overview	10

3.2.	Scope of the project	13

3.3.	Socio economic benefits (purpose) of the project	13

3.4.	Undesired impacts of the project	14

3.5.	Sources of funding and project cost	14

3.6.	Project duration	14

4.	Disclosure of procurement and Contract for Information Consultancy	15

4.1.	Disclosures of procurement information	15

4.1.1.	Overview of the procurement process	15

4.1.2.	Verification of the disclosed procurement information	16

4.1.3.	Analysis of the disclosed procurement information	18

4.2.	Disclosure of contract information	20

4.2.1.	Overview of the contract	20

4.2.2.	Verification of the disclosed contract information	21

4.2.3.	Analysis of the disclosed contract information	22

5.	Disclosure of procurement and contract information for works	23

5.1.	Disclosures of procurement information	23

5.1.1.	Overview of the procurement process	23

5.1.2.	Verification of the disclosed procurement information	23

5.1.3.	Analysis of the disclosed procurement information	23

5.2.	Disclosure of contract information	32

5.2.1.	Overview of the contract	32

5.2.2.	Verification of the disclosed contract information	32

5.2.3.	Analysis of the disclosed contract information	32

6.	Conclusion and Recommendation to the MSG	35

6.1.	Conclusion	35

6.2.	Issues Recommended for further review	35

# List of Tables

Table 1. Project description	10

Table 2. Technical and Financial Result	12

Table 3. Original contract amount, scope and contract period	13

Table 4. Consultants pass for technical and financial evaluation	17

Table 5. Consultant names, technical and financial evaluation result.	21

Table 6. Original scope of contractors, contract amount and project name	26

Table 7. Table price escalated in Basic Materials List	27

Table 8. Payment before any price adjustment.	28

Table 9. Main contract, Variation and Price Adjusted payment	28

Table 10. Payment before any price adjustment.	29

Table 11.  Main contract, Variation and Price Adjusted payment	29

Table 12.  Payment before any price adjustment	30

Table 13.  Main contract, Variation and Price Adjusted payment	30

Table 14.  Payment before any price adjustment.	31

Table 15. Main contract, Variation and Price Adjusted payment	31

Table 16.  Actual completion, delay, justified and unjustified days of delay	34

Table 17.  Disclosure of Procurement Information (44 Items)	36

Table 18.  Disclosure of Procurement Information (26 Items)	43

# Acronyms

AAHCPO - Addis Ababa Housing Construction Project Office

AP- Assurance Professional

CoST - Construction Sector Transparency Initiative

EIA - Environmental Impact Assessment

ETB - Ethiopian Birr

FDRE - Federal Democratic Republic of Ethiopia

FPPAA Federal Public Procurement and Property Administration Agency

IDS- Infrastructure Data Standard

MoE- Ministry of Education

MoU-Memorandum of Understanding

NMSGEC - National Multi-Stakeholder Group Executive Committee

PE - Procuring Entity

PLC - Private Limited Company

RAP - Resettlement Action Plan

RFP - Request for Proposal

ToR – Terms of References

VAT - Value Added Tax

# Executive Summary

The aim of the Construction Sector Transparency Initiative (CoST) is to enhance transparency of the procuring Entities (PEs), in areas of consultancy services and construction works. This is done by disclosing to the public, the way procurements are undertaken by public funds in the construction sector, Infrastructure Data Standard (IDS) at all stages of the consultancy as well as the construction project cycle. In fact the process shall be done from initial development of the project to the final completion; and the process shall also include service provision, impact assessment, feasibility study and construction contract.

Expansion of education is one of the major government agenda in its effort of attaining rapid socio-economic development in the country through Growth and Transformation Plan (GTP). To this end the government is expanding educational services, among other things, by opening new higher education institutions in the various corners of the country. Assosa University is among the 10 new universities opened recently, and for which constructions are undertaken for dormitory purposes. To this effect, the Ministry of Education has allocated sufficient budget to finance consultancy and construction works for dormitories and other associated projects of the aforementioned university.

Based on the Memorandum of Understanding (MoU) reached between CoST-Ethiopia and the Ministry of Education (Assosa University), Phase Four Dormitory Building Construction for Assosa University has been evaluated mainly on disclosure of information and project identification. In this project three service contracts were signed with four contractors who are engaged in dormitory construction. The service and work contracts are briefly described as follows:

Service Contract 1. Standard Design and Tender document preparation for Ten Universities. This service contract has been done during phase one of the design period by MH Consulting PLC, which was envisaged to be carried out in 6 month time with a contract amount of 6,667,493 ETB.

The original contract price of the agreement that was signed between the Ministry of Education and MH Engineering PLC, for standard design and tender document preparation was a lump sum of  6,667,493 ETB ( six million  six  hundred sixty seven thousands and  four hundred ninety three ETB),  including 15% VAT and other taxes. Other than the above stated consultancy services, there is no information related to consultancy services on studies related to: environmental and social impact assessment, environmental protection, resettlement action plan and mitigation measures on surrounding areas during and after the construction of the dormitories.

Services Contract 2. This part comprises of design review, supervision and contract administration services, and it has been handled by SG Consulting Engineers PLC. The design review supervision and contract administration has been taken until provisional acceptance took place.

Services Contract 3. For this service Habtamu International Consulting Architects and Engineers PLC signed the main agreement on 21 December, 2016. The service consists of: design review, supervision and contract administration for class rooms, dormitories, president’s residence, teachers’ residence, laboratory and workshop buildings. The consultant also signed supplementary agreement with Assosa University for contract administration and supervision services during final acceptance of completed dormitory buildings constructed by contractors namely: Radar, United, Dainel Tsegaye and Kidane Berihu.

Work Contract for Phase Four Dormitory Construction Projects. During the construction process, four contractors were engaged only in dormitory construction; and all of them completed the construction work; and accordingly provisional acceptance letter has been given. The final acceptance letter will be given to these construction companies after the final maintenance period is matured.

The selection process of contractors was done based on direct selection process by taking into account their pervious track records in construction completion performances. Here it is the Addis Ababa Housing Development Project Office that directly nominated contractors and subsequently sent their names to the university.

The performance of service provision and work contracts in light of cost, time and scope performance indicators:-

The assignment of the project includes the following activities:

- Services Contract I, Standard Design and Tender Document Preparation for Ten Universities is handled by MH Consultant;

- It is observed that Service Contract II, Design Review, Supervision and Contract Administration is handled by SG Consultant; and during the assessment there were significant changes in total amount contract cost and contract duration but there is no change in scope.

- Services Contract III, Supervision of final acceptance is handled by Habtamu International PLC.

- The work contract, the construction dormitory by four contractors.

With regard to consultancy services and construction of dormitory  in phase four, the following issues  are explain based on findings during disclosure time:

- Procurement process of service contract I

The major documents (such as minutes, selection criteria, negotiation letter, award letter, contract document and the ToR), which are important to understand the tender process and the overall consultancy services, are not available by the PE. The incompleteness and absence of the documents make it more difficult to deliver full information by the Assurance Professional. In this regard the Assurance Professional has faced challenges to assure service contract I; which on the other hand makes services contract I incomplete. The only available document is a letter which shows the contract amount. There is no any document that tales about the change of cost and scope during service contract period. The details are stated in chapter 3 and 4.

- Procurement process of service contract II

The same as service contract I, major documents for service contract II (such as advertisement on the newsletter, registration record of the contractor who purchased and submitted the tender document, tender evaluation criteria) which are important to understand the tender process, are not available by the PE. The only available document is technical evaluation result and the financial offer. The incompleteness of the documents makes it more difficult to deliver full information by the Assurance Professional. In fact the Assurance Professional faces challenge to assure the purchase process of services contract II because of absence of such documents. The only available document is the contract agreement and evaluation result. There is no any document that tales about change of scope, despite the significant change made in the consultancy fee compared to the total contract amount. The details are stated in chapter 3 and 4.

- Procurement process of service contract III

The same as service contract I and II, major documents for contract III, such as: advertisement on the newsletter, registration record of the contractor who purchased and submitted the tender document, tender evaluation criteria which are important to understand the procurement process are not available by the PE. In this respect the existing documents are not complete to justify the completeness of the procurement process; and thus the Assurance Professional faces challenge in assuring the completeness of the purchasing process of services contract III. The only available document is the contract agreement and evaluation result. There is no any document that tales about change of scope and contract amount. The details are stated in chapter 3 and 4.

Procurement process of work contract

The procurement process of work contract is undertaken based on the contractor’s pervious performance in Housing Development Project. Documents such as: minutes, selection criteria, negotiation letter in unit rate, award letter, which are important to understand the procurement process, are not available in the hands of PE. Incompleteness of the procurement documents makes it more difficult to the Assurance Professional to clarify the tender processes.

- United Construction PLC

The main contract amount was 19,587,469 ETB, the variation order number is 1,445,926.3 ETB; and the adjusted price 2,243,571.9, including 15% VAT. The total amount of payment effected is 23,273,967.2 including 15%VAT ETB. The contract period based on the agreement was from April 17/2015 – Jan 16/2016; but provisional acceptance was given on October 29/2016. There was significant delay in undertaking the construction; and the reason behind the delay is not justified and documented in detail. The only justified days listed in the provisional acceptance letter.

- Rader  Construction

The main contract amount was 25,565,056.99 ETB; the variation order number is 92,803.39 ETB; and the adjusted price is 3,407,457.27, including 15% VAT. The total amount of payment effected is 29,065,317.84 ETB. The number of justified days for the delay is 234 days, and the unjustified days of delay are 26 days. The contract period based on the agreement was from April17/2015 – January 16/2016; but provisional acceptance was given on 17 Sept. 2016. There was significant delay in undertaking the construction; and the reason behind the delay is not justified and documented in detail. The only justified days listed in the provisional acceptance letter.

- Daniel Tsegaye Contractors

The main contract amount was 25,565,056.99 ETB, the variation order number is 1,497,462 ETB; and the adjusted price is 2,728,408 including 15% VAT. The total amount of payment effected is 29,790,927.84 ETB. The number of justified days for the delay is 264 days, and the unjustified days of delay are 15 days. The contract period based on the agreement was from April 17/2015 – Jan. 16/2016; but the provisional acceptance was given on October 29/2016. There were significant delays in undertaking the construction; and the reason behind the delay is not justified and documented in detail. The only justified days listed in the provisional acceptance letter.

- Kidber Contractors

The main contract amount was 21,748,910.45 ETB, the variation order number is 273,444.34 ETB, and the adjusted price is 2,354,283.07 including 15% VAT. The total amount of payment effected is 24,376,637.86 ETB. The number of justified days for the delay is 264 days, and the unjustified days of delay are 15 days. The contract period based on the agreement was from April 17/2015 – Jan. 16/2016; but the provisional acceptance was given on October 29/2016. There were significant delays in undertaking the construction; and the reason behind the delay is not justified and documented in detail. The only justified days listed in the provisional acceptance letter.

Price adjustments were made because of change of the prices of basic materials, which are listed in Table 7.

- Implementation of service contract I, II & III

During the assessment time by the Assurance Professional, no document was found in the office of the PE that justifies change of scope during the contract period.

- Implementation of  work contract

During assessment time, it was observed that the contract was very much delayed-by 204% of elapsed time; and also there was significant change in the contract scope, time and cost due to additional works executed by all contractors.

- General

The AP tried to get all the necessary procurement documents from the PE, but only few documents such as contract agreements of all the consultants as well as contractors’ evaluation result for service contract II & III are available. Of course the contract agreements are available for both service contracts and work contracts except for service contract one. The procurement process was restricted with fixed unit rate for work contract, and as a result there was no competition. All the contractors completed their respective works, during the assurance period; and the final acceptance is under process.

# Introduction

The construction sector in Ethiopia plays a vital role in supporting social and economic development of the country and is making major contribution to the economic growth and poverty reduction of the country. However, mismanagement and corruption during planning and implementation process of construction projects could adversely affect the expected social and economic benefits.

The Construction Sector Transparency Initiative (CoST) is a multi-stakeholder initiative designed to increase transparency and accountability in the construction sector. In this respect, the mission of CoST is to enhance the transparency of a Procuring Entity (PEs) and construction companies by disclosing to the public information on construction projects at all stages of the project cycle - from initiation to final completion.

It is, however, recognized that the disclosure of this information on its own may not be sufficient in achieving greater accountability. This is because some of the information is likely to be complex and may not be understandable to the general public. An independent Assurance Professional (AP) is therefore appointed by the National Multi-Stakeholder Group Executive Committee (NMSG - EC) that will be responsible for assessing the adequacy and reliability of the disclosed project information and audit processes. Through periodic reporting system, the Assurance Professional will play an interpretative role in making data disclosures intelligibly understandable to the wider stakeholders in plain language.

A number of projects associated with housing construction, water development, road construction, etc. have been identified by NMSG-EC of CoST-Ethiopia. This report is therefore produced for Phase Four Dormitory Building in Assosa University, and it is prepared by the Assurance Professional, Demelash Betemariam.

Expansion of education is one of the major government agenda in an effort of attaining rapid socio-economic development in the country through Growth and Transformation Plan (GTP). To this end the government is expanding educational services, among other things, by opening new higher education institutions in the various corners of the country. Assosa University is among the 10 newly established universities for which constructions have been undertaken to provide the beneficiaries of education with the necessary facilities, amongst which are dormitories and associated facilities.

## Objectives of the Assignment

As described in the introduction part of this report, the Procuring Entities (PEs) are required to release information about the desired projects. In order to ensure the authenticity and acceptability of the information released by the Procuring Entities, it has to be analyzed and verified by experts of Assurance Professional who are appointed by the National Multi – Stakeholder Group Executive Committee (NMSG-EC) to look after the process of biddings and contract administration of such projects.

The objective of the assignment is therefore to evaluate the process followed by the procuring body and the level of transparency and governance of the on-going or accomplished projects. In this regard, the Assurance Professionals has two tasks: in the first place, they collect information and verify that the Infrastructure Data Standard (IDS) is both complete and accurate, and secondly the AP analyzes the disclosed data and interprets it so as to assure that the report is easily understandable by the wider public.

In general, the AP has to verify the source of the reports and has to confirm that the information is complete, accurate, and it is the latest version available by the time the report has been prepared.

The Quality Assurance Professional (QAP) has been appointed to achieve the following core objectives of the assurance process is to:

- Assure the accuracy and completeness of IDS disclosures by the PE;

- Summarize extent and accuracy of information released for the selected CoST project;

- Analyze the disclosed and demonstrate data in order to make informed judgments about the cost, time and scope aspects of the CoST Project; and

- Organize and produce a report that are clearly intelligible to the non-specialist with plain language, by outlining the findings regarding the implementation process; and thereby highlights any concern of the projects through detail analysis of information of such CoST Projects.

The challenges of the assurance process are:

- Some of the documents such as:  advertising paper, ToR, RFP, number of consultant and contractor who purchase and submit bid documents, evaluation criteria, disclosing system, contract document, bank guarantee, action plan, environmental impact assessment and mitigation measures   during and after construction of projects are not fully available in the hands of the procuring entity;

- Newly joined professionals of the procuring entity have little information about the Phase Four Project mainly because of absence of some important  documents pertaining to the project;

- Documents pertaining to the project are not properly handled as a result they are found in a scattered manner and are not easily accessible;

- Because of absence of all the necessary documents, we could not justify or understand why time extension and delayed price adjustment was given to the contractors.

# Disclosure of Project  Information

## Project overview

The dormitory construction project is completed and provisional acceptance was given a year ago. Currently preparation is underway to give final acceptance and to this effect contractors are doing minor rehabilitation works. At present students in the main campus are getting dormitory services from the newly built buildings. Detailed engineering design and tender document for the project were prepared by MH Consultant and subsequently submitted to the Ministry of Education (MoE). The design review, supervision and contract administration has been undertaken by SG Consultant and the final acceptance work was managed by Habtamu International Consulting Architects and Engineers PLC. The government of the FDRE, represented by MoE, had allocated sufficient budget to finance payments for consulting services and work contracts forming parts of the implementation process of the projects of which important features are given in Table 1 below:

Table 1. Project description

| No | Particulars | Description |
| --- | --- | --- |
| 1 | Project name | Assosa University , Dormitory Construction |
| 2 | Region | Benshangule Gumize Regional State |
| 3 | Zone | Assosa City Administration |
| 4 | City | Assosa |
| 5 | Project owner | Assosa University |
| 6 | Number of consultant | Three |
| 6.1 | MH Consultants PLc | Standard design and tender document preparation for Ten Universities |
| 6.2 | SG Consultants PLc | Design review, supervision and contract administration |
| 6.3 | Habtamu International Consulting Architects and Engineers PLC and lately changed its name to ASPIRE AECOM Architects and Engineers PLC, but there is no legal document that indicates the changed company’s name. | Supervision for Final Acceptance |
| 7 | Name of Contractors | Contracted dormitory |
| 7.1 | United Building Contractor | Lot 5 – Dormitory ( Do-T2) TV-210 and Do-T2-Tv-211) |
| 7.2 | Radar Building Contractor | Lot 1- Dormitory ( Do-T2-Tv, DO-T4-202 and DO-T2-TV-203 |
| 7.3 | Daniel Building Contractor | Lot 4 - Dormitory ( DO-T4-Tv-208, Do-T2/Tv-209 and Do-T4-213 |
| 7.4 | Kidane Berihu Building Contractor and lately change its name to Kidber Building Contractor, but there is no legal document that indicates the changed company’s name. | Lot 2 Dormitory ( Do-T4-Tv-200, Do-T4-206 and Do-T2 (miir( -Tv-207) |

The assignment of the project includes the following activities:

- Standard design and tender document preparation for Ten Universities handled by MH Consultant;

- Design review, supervision and contract administration handled by SG Consultant;

- Supervision of final acceptance handled by Habtamu International Consulting Architects and Engineers PLC ; and

- Work contract undertaken by: United Building Contractor, Radar Building Contractor, Daniel Building Contractor and Kidane Berihu Contractor.

The MH Consultant is in charge of undertaking consultancy service in standard design and tender document preparation; and the consultancy service period is 6 months. The consultant has undertaken his duty and responsibility within the given time frame and as a result he properly managed his assignment before the commencement of Phase Four contract agreement. In this respect, the standard design and tender document preparation by MH Consultant has successfully been done. In fact the inputs of MH Consultant in Phase Four Dormitory construction are standard design and tender document only.

After receiving the design and tender document from MH Consultant, the university carried out advertisement for design review, supervision and contract administration consultancy services. Even though the advertisement date and the newspaper, on which the advertisement was notified, is not available in the PE. The PE tender committee receives the technical and financial proposal from SG Consultant, Virtual Consultant, Acute Engineering Consultant, Dynamic Planner Consultant and Yohanes Abay Consultanting Engineers and Architects. Among them Virtual and Acute Consultants submitted copy of the document in one post instead of independently submit their respective copies in separate posts. On the other hand Yohanes Abay submitted the original document instead of a copy. It is worth noting that submission of two original documents does not qualify a candidate to pass to the next step, i.e. technical evaluation. In this regard only Dynamic Planner Consultant and SG Consultant were qualified for technical evaluation. The financial offering of the consultants is stated as follow:

- SG Consultant         2,058,500.00  ETB

- Dynamic Planner      3,481,641.20 ETB

It was SG Consultant that finally became the winner and subsequently signed the contract agreement with the University on May 08/2015; and the assignment was to be completed in a contract period of 24 months. Under the consultancy period, the consultant not only the consultancy services for listed contractors but also there are others constructors which are not include in our assessment assignment. During the consultancy period, the consultant undertook only design review, supervision and contract administration until the provisional acceptance was done. Thus, the final acceptance supervision and contract administration is not included in the contract.

Assosa University had made invitation to consultants through Addis Zemen newspaper, dated on August 6, 2016 (ሓምሌ 30/2008 ዓ.ም) for those that had interest to enter into a bid to undertake new design work, design review, supervision and contract administration for different construction projects. During the invitation 13 consultants submitted their technical and financial proposals; and from among the 13 consultants only 4 of them passed the technical evaluation. Accordingly, final evaluations on both technical and financial proposals were made and the final winner of the bid became Habtamu International Consulting Architects and Engineers PLC. The firm subsequently signed an agreement with the client and the contract was awarded to the winner firm to undertake the assignment as has been stated above.

Table 2. Technical and Financial Result

| Name of Consultant pass for Technical and Financial Evaluation | Technical Evaluation Result from 80% | Offered price | Financial Result out of 20% | Sum of technical and Financial results out of 100% | Remark |
| --- | --- | --- | --- | --- | --- |
| ETG Designs and consultants Plc | 70.4 | 5,427,425 | 8.98 | 79.38 | Habtamu International consulting Architects and Engineers PLC is the winner |
| Habtamu International Consulting Architects and Engineers PLC | 66.4 | 2,438,000 | 20 | 86.4 |  |
| Yohannes Abay consulting Architect & Engineers | 64.8 | 5,168,100 | 9.43 | 74.23 |  |
| Virtual Consulting PLC | 64.4 | 2,663,515 | 18.30 | 82.7 |  |

Instead of inviting new consultant, the university decided to sign supplementary agreement with Habtamu International Consulting Architects and Engineers PLC for supervision and contract administration of final acceptance of Phase Four Dormitory project. The period allotted for final acceptance processing is not more than one month and final minor rehabilitation process shall be undertaken during study period.

The scope of contactors is construction of dormitory within 270 days. The following table describes the time frame along with the estimated original contract cost of each contractor involved in the project.

Table 3. Original contract amount, scope and contract period

| Description | Contractors Name |
| --- | --- |
|  | United | Radar | Daniel | Kidane Berihu |
| Project Name | Lot 5 – Dormitory ( Do-T2) TV-210 and Do-T2-Tv-211) | Lot 1- Dormitory ( Do-T2-Tv, DO-T4-202 and DO-T2-TV-203 | Lot 4- Dormitory ( DO-T4-Tv-208, Do-T2/Tv-209 and Do-T4-213 | Lot 2 Dormitory ( Do-T4-Tv-200, Do-T4-206 and Do-T2 (miir( -Tv-207) |
| Original contract and Estimated budget in ETB | 19,587,469.02 including VAT 15% | 25,565,056.99 including VAT 15% | 25,565,056.99 including VAT 15% | 21,748,910.45 including VAT 15% |
| Date of the Signing of the agreement | 17 April/2015 | 17 April/2015 | 17 April/2015 | 17April/2015 |
| Contract period | 17April/2015 – Jan 16/2016 | 17 April/2015 -– Jan 16/2016 | 16 April/2015– Jan 15/2016 | 17 April/2015– Jan 16/2016 |
| Project scope | 270 days | 270 days | 270 days | 270 days |

## Scope of the project

The scope of the project for construction of student dormitories in Assosa University was within 270 calendar days.

## Socio-economic benefits (purpose) of the project

The project could have positive socio-economic impacts in many respects. In the first place it solves the problem of dormitory for students that have been getting educational services in the aforementioned university. This in turn would have positive impact on the overall academic performance of the students under discussion. The other impact is that the project could create temporary and permanent employment opportunities for residences of the town and also creates opportunities for skill transfer. This is to say that temporary jobs could be created for some job seekers during the construction period. On the other hand permanent jobs would also be created for those who could be engaged in sanitary and security services within the university. Likewise, workers who are employed in the project would develop their skills related to the construction works.

## Undesired impacts of the project

There are not as such significantly observed undesired impacts of the project. However, one thing that should be worth mentioning is that there could be some environmental impacts of the project during the construction period because some construction materials, in the form of cart away, could be dumped in the vicinity of the university as a result of which it could adversely affect the environment resulting in siltation on rivers and streams during rainy seasons. On the other hand dust from construction sites would also negatively affect the environment and hence the community during construction period.

## Sources of funding and project cost

The source of funding is the government of Ethiopia through its affiliated ministry, the Ministry of Education.

## Project duration

The construction period set for each (four of them) contractors is 270 days; and for further details refer to Table 3 above.

# Disclosure of procurement and Contract for Information Consultancy

## Disclosures of procurement information

### Overview of the procurement process

The procurement process of consultancy services have three major assignments, and in each assignment three different consultants perform the overall project assignment; and these assignments are consultancy services on detailed engineering design and supervision and contract administration. In this regard, the original scopes of the consultancy services are:

- Engineering design, this is to carry out standard design and tender document preparation handled by MH Consultant;

- Design review, supervision  and contract administration work was handled by SG Consultant; and

- Supervision for final acceptance is handled by Habtamu International Consulting Architects and Engineer PLC.

The contract period for standard design and tender document preparation is six months. The consultant has been doing his duties and responsibilities during his contract period. The supervision and contract administration has been done for other projects, not for Phase Four Dormitory. MH Consultant had input only in the preparation of standard design and tender document preparation for Phase Four Dormitory, but did not participate in the design review, supervision and contract administration, because SG Consultant handled the design review, supervision and contract administration.

Generally, the standard design and tender document preparation was completed by MH Consultant; while the supervision and contract administration service was handled and completed by SG Consultant. The remaining supervision and minor rehabilitation works for final acceptance, after defect liability period, was supervised by Habtamu International Consulting Architects and Engineer PLC with a cost of 414,460 (four hundred fourteen thousands four hundred sixty ETB), and this was be undertaken in almost one month time.

### Verification of the disclosed procurement information

MH Consultant has been engaged in standard design and tender document preparation of Assossa university right from the time of its establishment. The Consultant received all the above assignments through single selection processes and negotiation. For finalization of Phase Four Dormitory Project, the Consultant also prepared standard design and tender documents.

The university made a call for consultants to undertake design review, supervision and contract administration. Based on the invitation, five consultants submitted their respective technical and financial proposals; and the consultants were:

- SG Consultant;

- Acute Consultant;

- Virtual Consultant;

- Dynamic Planner Consultant; and

- Yohanes Abay Consulting Architects & Engineers.

The evaluating committee evaluated the documents of the above five consultants; and among them Virtual and Acute consultants were automatically rejected for not respecting the procedure of tender document submission. Both these consultants submitted their respective copies of tender documents in a single post instead of submitting them in separate posts. On the other hand Yohanes Abay also submitted two original documents instead of a copy and an original and as the result it was also rejected. Here attempt was made to check whether or not this criterion (related to submission of documents) is present in the directive of the evaluation criteria, but the evaluation criteria document was not available during our assessment period in the procurement office.

The evaluation process had two steps - one technical and the other financial. Accordingly, two consultants passed the technical evaluation, and subsequently their respective financial proposals were directly opened. SG Consultant was the list bidder and as a result he became the winner as has been shown in the table 4:

Table 4. Consultants pass for technical and financial evaluation

| No | Name of consultant | Offered price | Remark |
| --- | --- | --- | --- |
| 1 | SG Consultant | 2,058,500.00 | List bidder and winner |
| 2 | Dynamic Planner | 3,481,641.20 |  |

For the final acceptance, the university simply made supplementary agreement with Habtamu International Consulting Architects and Engineer PLC, while this consultant already had other agreement and assignment for design, supervision and contract administration works in the University. Instead of recruiting other consultant for one month work, the University merely choose supplementary agreement with the existing consultant (Habtamu International Consulting Architects and Engineer PLC) for an assignment that amounts to 414,460 ETB (Four hundred fourteen thousand four hundred sixty ETB).

#### 4.1.2.1. Completeness of the disclosed procurement information

As far as completeness of disclosing procurement information is concerned, so far full information is not available. In fact the procurement process was handled by the Ministry of Education (MoE); and the Ministry has only the contract agreement between MoE and MH Consultant and the invitation letter that calls for submission of the financial proposal. Other documents such as the minutes that deal with the selection process and the justifications given are not available. The only documents which are available in the procurement office of the university are those which are related to the contract agreement and tender committee valuation result. Other documents that show the process of tendering such as: when the advertisement was made, bidders expression of interest, the number of technical and financial proposals submitted by consultants, the names of bidders that attended at the closing and opening periods of bid documents, the process of disclosure of bid documents and the presence (if any) of complaint before the opening of the financial proposals.

In fact the university advertised the job on Addis Zemen Gazetta on August 6, 2016 (ሀምሌ 30/2008 ዓ.ም); and subsequently five consultants submitted their technical as well as financial proposals. Out of the five bidders only two of them were elegible for the financial evaluation.

#### 4.1.2.2. Accuracy of the disclosed procurement information

With regard to accuracy of the disclosed procurement information, the process of procurement related to MH Consultant PLC is clear because it was done through the process of direct selection and negotiation. But, as have been mentioned above, there is no full information (in the absence of all the necessary documents) as to when the advertisement was took place, and the selection criteria for selecting the consultants. The other two consultants also have no full procurement document such as evaluation criteria and the technical proposal submitted by the consultants.

### Analysis of the disclosed procurement information

#### 4.1.3.1. Compliance of the procurement process with rules of advertisement

The procurement process lacks some procedural aspects right from the time of advertisement to final award of the assignment. Here the Assurance Professional tried to get all pertinent documents related to the procurement process, but as stated above, all the necessary documents are not available and as a result it has become difficult to prove whether or not the procurement process is in compliance/harmony/ with the established rules and procedures of the procuring entity.

#### 4.1.3.2. Efficiency of the procurement process (Timeliness)

To exhaustively examine the efficiency (timeliness) of the procurement process all the necessary documents that describe the process right from the date of advertisement to the signing of the contract agreement should be available. But as have been mentioned above, such documents are not available in the office of the procurement entity and as a result it is difficult to forward comments on such issue. One thing apparently observed from available documents is that the time span between the start of the evaluation process to that of the signing of the contract agreement for SG Consultant took three months, i.e. from 16 March, 2015 to 08 May, 2015; and this seems to me a reasonable time. But there is no as such information about the validity of the bid period in the absence of the bid document during the assessment period.

With regard to the procurement process of SG Consultant, the evaluation committee checks whether the consultant properly submitted the technical and financial proposals on 07/07/2007 E.C. Out of the five bidders three consultants could not pass to the next step (financial evaluation) and only two of them manage to pass the technical evaluation. The tender committee opened the financial proposal on 13/08/2007 E.C, and accordingly SG Consultant become the winner. SG Consultant signed the agreement with Assosa University on May 08, 2015. Of course no document is found that tells us when the advertisement for this bid was made. All we know is the duration from the start of evaluation to the signing of the contract agreement which is from March16 /2015 up to May 08/2015; and thus the procurement process was completed in about two month time.

During the selection of Habtamu International Consulting Architects and Engineers PLC, the advertisement was disclosed on 30/11/2008 E.C. In this bid thirteen consultants competed and only four of them passed the technical evaluation which was disclosed on 26/1/09 E.C. Finally, the aggregate result of both technical and financial evaluations was disclosed on 10/04/2009 E.C. The supplementary agreement signed Assosa University and Habtamu International Consulting Architects and Engineer PLC only for final acceptance. The time taken for the procurement process was from 30/11/2008 E.C. to 10/04/2009 E.C. The total time taken for the procurement process was about five months. Thus, significant days were consumed to complete procurement process.

#### 4.1.3.3 Fairness of the procurement rules on participation

All the necessary documents that deal with the technical proposals of the consultants are not available and as a result it has become difficult to evaluate the fairness and the level of participation of bidders in the evaluation process.

#### 4.1.3.4 Transparency on tender evaluation process

Documents related to invitation letter, evaluation criteria, issues raised during bid opening or disclosure of evaluation results and responses made to complaints, technical proposals as well as full evaluation documents of the consultants are not available. As the result of which it has become difficult to clearly understand the level of transparency of the bidding and evaluation process.

#### 4.1.3.5 Objectivity of the tender evaluation and the award criteria

The objective of tender evaluation and the award criteria are in order to bring about fair competition and transparency in the tendering process.

#### 4.1.3.6 Competitiveness of the award price

Habtamu International Consulting Architects and Engineer PLC and SG Consultant offered least prices. Moreover, the prices of these consultants were reasonable enough as compared to the prices offered by the other consultants.

#### 4.1.3.7 Overview of contract milestones: Original Scope, Time and Cost

MH Consultant PLC signed the agreement for standard design and tender document preparation. The original scope is clearly set in the contract document which is preparation of standard design and tender document in six month time with contract amount 6,667,493 ETB.

In the original scope SG Consultant was assigned to undertake the assignment in two year time - from May 08/2015 to May 07/2017.  The assignment was not only design review, supervision and contract administration for Phase Four selected  contractors (Rader, United, Daniel Tsegay and Kidbar), but also on other contractors too namely: Kiros Hadego Building Contractors, Semere Kale Construction, Neguse Kelelome General Contractors and Milk Construction. The consultant provided the service up to October 2018, i.e. until provisional acceptance was given. The total time extend until October 2018 almost the consultant give the services for additional 16 month (67% the contract period). The procuring entity effected an additional payment of 1,372,320.00 ETB (67% of the contract amount).

Habtamu International Consulting Architects and Engineer PLC signed the agreement with the University under main contract. Assossa University signed supplementary agreement with the consultant to undertake supervision and contract administration during the final acceptance processes; and for this assignment the consultant signed the agreement on February 15, 2018.

## Disclosure of contract information

### Overview of the contract

The procurement process for the standard design and tender document preparation was made though single selection process and negotiation with MH Consultant PLC. In fact MH Consultant did not participate in the design review, supervision and contract administration of Phase Four Dormitory Construction project; rather it was involved only in standard design and tender document preparation. The university invited new consultants for design review, supervision and contract administration for Phase Four Dormitory Construction project. Accordingly, the consultants who submitted their technical and financial proposals were:

- SG Consultant;

- Acute Consultant;

- Virtual Consultant;

- Dynamic Planner Consultant; and

- Yohanes Abay Consulting Architects & Engineers.

The evaluation committee undertook evaluation on the above five consultants. As has been mentioned above, from amongst them Virtual, Acute and Yohanes Abay Consultants were automatically rejected for not keeping the procedure of submission of tender documents. As a result three of them failed to pass the technical evaluation. Here it is worth mentioning that no document is found in the office of the procuring entity that describes the evaluation criteria.

On August 6, 2016 (ሀምሌ 30/2008 ዓ.ም) the University invited for interested consultants, through Addis Zemen Gazette, and as the result 13 consultants showed interest for the assignment. From amongst them only five consultants passed the technical evaluation. Four of them are listed in the following table along with their respective technical and financial results:

Table 5. Consultant names, technical and financial evaluation result.

| Name of Consultant | Technical result from 80% | Offered cost | Financial result (20%) | Technical and Financial Result | Remark |
| --- | --- | --- | --- | --- | --- |
| Yohannes Abay Consulting Architect & Engineers | 64.8 | 5,168,100 | 9.43 | 74.43 |  |
| ETG Designs and Consultants PLC | 70.1 | 5,427,425 | 8.98 | 79.38 |  |
| Virtual Consulting PLC | 64.4 | 2,663,515 | 18.30 | 82.7 |  |
| Habtamu International Consulting Architects and Engineers PLC | 66.4 | 2,438,000 | 20.00 | 86.4 | List bidder, winner |

### Verification of the disclosed contract information

#### Completeness of the disclosed contract information

The contract document between the consultant and PE is complete which incorporates all the necessary rights and enforcement rules and regulations.

#### Accuracy of the disclosed contract information

The disclosed contract document between the consultant and the PE was accurate which incorporates all the necessary rights and enforcements.

### Analysis of the disclosed contract information

#### Issues related to contract price, duration and scope

#### The contract price for MH Consultant is 6,667,493 ETB; and preparation of standard design and tender document was done in 6 month time. The original contract duration for SG Consultant was for two years (from May 08/2015 up to May 07/2017) but the assignment is not only to supervise Phase Four selected contractors (Radar, United, Daniel Tsegay and Kidbar), but also Kiros Hadigo Building Contractors, Semere Kale Construction, Neguse Kelelome General Contractors and Milk Construction. The consultant gave the service up to October 2018, i.e. until provisional acceptance was done on the selected contractors. The total duration was until October 2018, and as the result the consultant gave the service for additional 16 month (67% the contract period). The procuring entity effected additional payment of 1,372,320.00 ETB (67% of the contract amount). The root causes for change of scope are variation and price adjustment.

Habtamu International Consulting Architects and Engineers PLC provided the consultancy service with an amount of 414,460 (Four hundred fourteen thousand four hundred sixty) ETB for a period of one month.  Yet, the consultancy service is not completed. The consultants supervise the final acceptance process during assessment period.

# Disclosure of procurement and contract information for works

## Disclosures of procurement information

### Overview of the procurement process

The procurement process was done based on the previous performances of contractors in Addis Ababa Housing Construction Project. As has been mentioned above, the Addis Ababa Housing  Construction office  sent a letter to Assosa University in a letter with reference number ቤ/ግ/ፕ 14/9560 dated on  March 31, 2015 (መጋቢት 22/2007 E.C); and four  contractors’ names (Rader, United, Daniel Tsegaye and Kidber) were included in the letter. According to Addis Ababa Housing Construction Project Office, the performances of the above-mentioned three contractors were more than 98%. It is with this selection background that Assosa University signed agreements with the four contractors. Please refer to annex 1 for the attached letter.

### Verification of the disclosed procurement information

As stated above, the selection process was made through recommendation letter based on pervious performances of contractors in Addis Ababa Housing Construction Project.

#### Completeness of the disclosed procurement information

The recommended contractors were notified whether to accept the invitation or not. The contractors accepted the fixed unit rate of each item and subsequently signed the agreement with the procuring entity.

#### Accuracy of the disclosed procurement information

Since the procurement was made through direct selection, nothing was needed as disclosed procurement information.

### Analysis of the disclosed procurement information

As has been mentioned above, the procurement process was through direct selection process, based on pervious performances of contractors in Addis Ababa Housing Construction Project office. So the procurement process was undertaken based on the modality of direct selection process and fixed unit rate.

#### Compliance of the procurement process with rules of advertisement

The procurement process complies with the rules of advertisement.

#### Efficiency of the procurement process (Timeliness)

No data is available to measure the efficiency/ timeliness of the procurement process.

#### Fairness of the procurement rules on participation

As long as selection of bidders based on their previous performances is set in the procurement rule, thus the process seems fair.

#### Transparency of the tender’s evaluation process

The bidders did not submit their respective costs, it is the procuring entity that directly awarded the project through fixed unit rate; and the contractors accepted the offered rate by the procuring entity and subsequently signed the agreement.

#### Objectivity the tender evaluation and the award criteria

The tender evaluation and award criteria is not necessary during this type of bidding processes, while the contractors were selected directly based on their pervious performances through fixed unit rate.

#### Competitiveness of the award price

The award price was made by the procuring entity based on fixed unit rate.

#### Overview of contract milestones: Original Scope, Time & Cost

The original scope for all the contractors to undertake construction of the dormitories was within 270 calendar days. But due to late decision on variation and price escalation, the assignment of each contractor was delayed on the average by 200 days. The original scope of contractors, contract amount and project names as well as provisional acceptance for each contractor are shown in Table 4.

The cost of construction falls in variation and price adjustment; and in fact the employer paid considerable amount of money for both the variation and adjusted prices. The contract document as shown in GCC.62 states that, price adjustment can be done on Basic Materials List; and GCC.15 notes that modification should be done by change order. The percentage of increment on each basic material is shown in Table 6.

GCC.62 declares about Price adjustment;

GCC.62.1   The contract is subject to price adjustment from the effective date;

GCC.62.7   The basis for compensation shall be merely through those categories of inputs which are specifically listed in the schedule of Basic Materials List.

GCC. 62.13

- The price adjustment factor shall consider only the list of items in schedule of Basic Materials List.

    - The price adjustment factor to payment amounts due shall be calculated based on the formula to be prepared by the contractor, checked and recommended by the consultant and approved by the employer.

    - The price adjustment formula approved by the employer shall be part of the contract agreement.

    - The contractor shall submit to the engineer price adjustment payments every six months.

GCC.15 Modification by change order

The special condition of contract did not specify about the variation, but in the general condition of contract about modification and change order is listed. The modification and change order should be made by the engineer and subsequently be approved by employer.

Table 7. Original scope of contractors, contract amount and project name

| Contractors Name | United | Radar | Daniel Tsegaye | Kidane Berihu |
| --- | --- | --- | --- | --- |
| Project Name | Lot 5 – Dormitory ( Do-T2) TV-210 and Do-T2-Tv-211) | Lot 1- Dormitory ( Do-T2-Tv, DO-T4-202 and DO-T2-TV-203 | Lot 4- Dormitory ( DO-T4-Tv-208, Do-T2/Tv-209 and Do-T4-213 | Lot 2 Dormitory ( Do-T4-Tv-200, Do-T4-206 and Do-T2 (miir( -Tv-207) |
| Original contract and Estimated budget in ETB | 19,587,469.02 including VAT 15% | 25,565,056.99 including VAT 15% | 25,565,056.99 including VAT 15% | 21,748,910.45 including VAT 15% |
| Sign the agreement | 17/ April/2015 | 17/ April/2015 | 17/ April/2015 | 17/ April/2015 |
| Site Handover |  | 20th April 2015 | 20th April/2015 | 17th April 2015 |
| Contract period | 17/ April/2015 – Jan 16/2016 | 17 April/2015 -– Jan 16/2016 | 16/ April/2015– Jan 15/2016 | 17/ April/2015– Jan 16/2016 |
| Project scope | 270 days | 270 days | 270 days | 270 days |
| Provisional acceptance | October 29/2016. (19/02/2009) | 17 Sept. 2016, | October 29/2016. (19/02/2009) | October 29/2016. (19/02/2009) |

Table 8.  Price Escalate in Basic Materials List

| No. | Item | Unit | Basic Price in ETB | New prices 24/11/2008 EC in ETB | Price in ETB | Price escalation |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Sand | M3 | 130 | 180 | 138.5% | 38% |
| 2 | Stone | M3 | 140 | 200 | 142.9% | 43% |
| 3 | Gravel | M3 | 420 | 480 | 114.3% | 14% |
| 4 | EGA 400 and 500, 0.4mm thick roof cover | Ml | 143.95 | 107.29 | 74.5% | -25% |
| 5 | G-28 GALVANIZED METAL SHEET | M2 | 117.29 | 100.14 | 85.4% | -15% |
| 6 | Steel structures (RHS) | Kg | 24.15 | 18.23 | 75.5% | -25% |
| 7 | Black Iron sheet 5,6 and 8 mm | kg | 22.56 | 20.40 | 90.4% | -10% |
| 8 | Black iron ribbed sheet 08 mm | M2 | 182.43 | 154.47 | 84.7% | -15% |
| 9 | Chip wood ceiling(1.25x2.5m) | pcs | 153.0 | 208.0 | 135.9% | 36% |
| 10 | Diesel fuel | Lit | 17.49 | 14.80 | 84.6% | -15% |
| 11 | Regular fuel | Lit | 19.41 | 17.25 | 88.9% | -11% |
| 12 | Carpenter | Day | 140.0 | 250.0 | 178.6% | 79% |
| 13 | Mason | Day | 140.0 | 250.0 | 178.6% | 79% |
| 14 | Daily labor | Day | 40.0 | 80.0 | 200.0% | 100% |

Here needs an introductory paragraph

- United Construction PLC

The contractor requested to the consultant price adjustment payment for the executed works in a letter with Ref. No. U/Con/1/032/09 dated on 01/06/2009 E.C. for price adjustment on interim payment Number 02,03,04,05 and 06. The total amount was ETB 2,109,674.19 (Two Million One Hundred Nine Thousand Six Hundred Seventy Four Birr and 19/100 cent) including VAT for the price escalated items. The escalated items are those which are shown in Table 7.

Table 9. Payment before any price adjustment.

| Payment No. | Net Payment in ETB | VAT 15% in ETB | Net payment + VAT 15% in ETB |
| --- | --- | --- | --- |
| 1 st Advance | 3,406,516.4 | 510,977.5 | 3,917,493.9 |
| Payment No 2 | 1,020,348.4 | 287,277.7 | 1,307,626.1 |
| Payment No 3 | 1,926,468.9 | 199,217.1 | 2,125,686.0 |
| Payment No 4 | 1,640,023.5 | 261,620.2 | 1,901,643.7 |
| Payment No 5 | 2,633,865.7 | 421,418.6 | 3,055,284.3 |
| Payment No 6 | 2,820,183.3 | 453,990.4 | 3,274,173.7 |
| Payment No 7 | 1,821,991.4 | 287,682.8 | 2,109,674.2 |
| Total | 11,862,881.20 | 1,911,206.80 | 13,774,088.00 |

Table 10. Main contract, Variation and Price Adjusted payment

| Item No | Description | Before Vat 15% in ETB | VAT 15% in ETB | Net payment + VAT 15% in ETB |
| --- | --- | --- | --- | --- |
| 1 | Main contract for Dormitory Do-T2 mirr-Tv-210 | 8,516,290.88 | 1,277,443.6 | 9,793,734.5 |
|  | Variation Order # 1 | 136,241.59 | 20,436.2 | 156,677.8 |
|  | Variation Order # 2 | 518,268.84 | 77,740.3 | 596,009.2 |
| 2 | Main contract for Dormitory Do-T2-TV-211 | 8,516,290.88 | 1,277,443.6 | 9,793,734.5 |
|  | Variation Order # 1 | 85,772.24 | 12,865.8 | 98,638.1 |
|  | Variation Order # 2 | 514,435.84 | 77,165.4 | 591,601.2 |
|  | Price adjustment for payment | 1,950,932.11 | 292,639.8 | 2,243,571.9 |
|  | Grand Total after deduction | 20,238,232.36 | 3,035,734.9 | 23,273,967.2 |

The final payment went up by 118.8%, more than the original contract provisional acceptance that was taken on October 29/2016.

- Rader  Construction

The main contract amount was 25,565,056.99 ETB; the variation order number 1 is 92,803.39 ETB and the adjusted price was 3,407,457.27 including 15% VAT. The total amount of payment effected became 29,065,317.84 ETB. The number of justified days of delay was 234 days and the unjustified days of delay were 26 days.

Table 11. Payment before any price adjustment.

| Payment No. | Net Payment in ETB | VAT 15% in ETB | Net payment + VAT 15% in ETB |
| --- | --- | --- | --- |
| 1 st Advance | 4,446,096.87 | 666,914.53 | 5,113,011.40 |
| Payment No 2 | 1,252,677.00 | 542,839.00 | 1,795,516.00 |
| Payment No 3 | 2,690,419.68 | 113,101.16 | 2,803,520.84 |
| Payment No 4 | 1,455,872.97 | 248,008.17 | 1,703,881.14 |
| Payment No 5 | 2,726,340.73 | 4304,74.85 | 2,726,340.73 |
| Payment No 6 | 4,021,271.86 | 634,937.66 | 4,656,209.52 |
| Total | 12,146,582.24 | 1,538,885.99 | 13,685,468.23 |

Table 12.  Main contract, Variation and Price Adjusted payment

| Payment category | Before 15% VAT in ETB | 15 % VAT in ETB | including 15% VAT in ETB |
| --- | --- | --- | --- |
| Main contract | 22,230,484.34 | 3,334,572.65 | 25,565,056.99 |
| Price adjustment Final Payment | 2,963,006.32 | 444,450.95 | 3,407,457.27 |
| Variation order | 80,698.77 | 12,104.82 | 92,803.59 |
| Total Sum | 25,274,189.43 | 3,791,128.41 | 29,065,317.84 |

- Daniel Tsegaye Contractors

Daniel Tsegay Building Contractor signed the agreement with Assosa University on 16th of April, 2015 with contract amount of 25,565,056.99, including VAT 15%. The site handover was taken place on 20th of April, 2015. The advance payment was 5,113,011.40 (Five million one hundred thirteen thousand eleven birr and 40/100 cents) ETB which was effected through unconditional bank guarantee from Abay Bank S.C with an amount of 5,113,011.40 (Five million one hundred thirteen thousand eleven birr and 40/100 cents) ETB. The total number of delayed days by this contractor was 279 calendar days, out of this 264 calendar days were justified and the remaining 15 calendar days were unjustifiable both by the consultant and the employer. For the unjustified delay there are no documents that indicate about the type of measure taken for delay.

Table 13.  Payment before any price adjustment

| Payment No. | Net Payment in ETB | VAT 15% in ETB | Net payment + VAT 15% in ETB |
| --- | --- | --- | --- |
| 1 st Advance | 4,446,096.87 | 666,914.53 | 5,113,011.40 |
| Payment No 2 | 5,749,569.59 | 931,877.94 | 6,681,447.53 |
| Payment No 3 | 1,637,018.70 | 279,731.04 | 1,916,749.74 |
| Payment No 4 | 5,687,748.14 | 905,294.99 | 6,593,043.13 |
| Payment No 5 | 2,253,902.5 | 355,879.33 | 2,609,781.83 |
| Total | 15,328,238.93 | 2,472,783.30 | 17,801,022.23 |

Table 14.  Main contract, Variation and Price Adjusted payment

| Payment category | Before 15% VAT in ETB | 15 % VAT in ETB | including 15% VAT in ETB |
| --- | --- | --- | --- |
| Main contract | 22,230,484 | 3,334,573 | 25,565,057 |
| Price adjustment | 2,372,529 | 355,879 | 2,728,408 |
| Variation order | 1,302,141 | 195,322 | 1,497,462 |
| Total Sum | 25,905,154 | 3,885,774 | 29,790,927 |

- Kidber Contractors

Variation number one for Dormitory Do-T4-206  in superstructure  concert work, formworks, deformed bars, and metal work, plastering and painting, finishing work, glazing and painting are listed in the payment certificate and variation number two for retaining wall of Dormitory Do-T2 mirr –TV- 207. Time extension 342 days ASu. po/ 2374/46/09 and date 16/10/2009 Ec accepted, in addition to this the contractor requested  Ref  No ASu Po 2449/11/09 date 04/11/09 142 days but get only 122 days accepted in addition  mobilization 15 date and 464 days total 479 days extended with acceptable ground. The provisional acceptance has been taken date 29/07/2009

Table 15.  Payment before any price adjustment.

|  | Net Payment in ETB | VAT 15% in ETB | Net payment + VAT 15% in ETB |
| --- | --- | --- | --- |
| 1 st Advance | 3,782,419.21 | 567,362.88 | 4,349,782.09 |
| Payment No 2 | 1,597,848.72 | 264,906.01 | 1,862,754.73 |
| Payment No 3 | 2,541,749.31 | 412,540.51 | 2,954,289.82 |
| Payment No 4 | 2,137,347.93 | 341,975.67 | 2,479,323.60 |
| Payment No 5 | 2,434,477.55 | 527,013.72 | 2,961,491.27 |
| Payment No 5 | 1108882.43 | 183659.72 | 1,292,542.15 |
| Payment No 6 | 1,755,497.90 | 277,183.88 | 2,032,681.78 |
| Total | 11,575,803.84 | 2,007,279.51 | 13,583,083.35 |

Table 16. Main contract, Variation and Price Adjusted payment

| Payment category | Before 15% VAT | 15 % VAT | Including 15% VAT |
| --- | --- | --- | --- |
| Main contract | 18,912,096.04 | 2,836,814.41 | 21,748,910.45 |
| Price adjustment No 1 | 1,847,892.53 | 277,183.88 | 2,125,076.41 |
| Price adjustment No 2 | 199,310.14 | 29,896.52 | 229,206.66 |
| Variation order 1 | 35,135.73 | 5,270.36 | 40,406.09 |
| Variation order 2 | 202,641.96 | 30,396.29 | 233,038.25 |
| Total Sum | 21,197,076.40 | 3,179,561.46 | 24,376,637.86 |

## Disclosure of contract information

### Overview of the contract

The contractors were selected based on their pervious performances on similar projects. Thus, the result of the procurement process was undertaken by restricted tender as a result the unit price was fixed by the employer.

### Verification of the disclosed contract information

Since contractors are already participating in different construction projects in Addis Ababa Housing Construction Agency, the disclosed contract information was done merely through notifying to contractors by a letter.

#### Completeness of the disclosed contract information

In the contract document signed between Assosa University and the contractors the scope of construction, unit rate of each construction item, the drawings and the site plan are explicitly written. Thus, the contract information is clearly disclosed.

#### Accuracy of the disclosed contract information

In the contract document all the rights and responsibilities of the parties involved are clearly stated. Moreover, it is also pointed out in the contract agreement how to manage any variation, price escalation as well as supplementary agreement for additional works.

### Analysis of the disclosed contract information

#### Issues related to contract price

The prices of some basic items such as: stone, sand, daily labor, carpenter and mason were revised five times, in 21/02/2008 E.C, 16/04/2008 E.C, 05/07/2008 E.C, 01/09/2008 E.C and 24/11/2008 E.C. In the report, it is noted that the root cause for price adjustment was increment in fuel price and the presence of massive construction projects in the surrounding areas. This massive construction in the surrounding areas absorbed the labor force such as carpenters as well as masonry workers. There is no unjustified change in the document, but the root cause for the delay is not supported by justifiable document.

#### Issues related to the contract duration

The contract duration for projects of all the four contractors was delayed by about 70% to 90% as compared with the original scope. There is no, however, sufficient justification/explanation behind the delay.

#### Issues related to contract scope

As has been mentioned above, the contract duration of the projects for all the four contractors was delayed by about 70% to 90% as compared with the original scope. But the reason that causes delay of the projects is substantiated through documents.

Table 17.  Actual completion, delay, justified and unjustified days of delay

| Contractors Name | United | Radar | Daniel Tsegaye | Kidane Berihu |
| --- | --- | --- | --- | --- |
| Sign the agreement | 17/ April/2015 | 17/ April/2015 | 17/ April/2015 | 17/ April/2015 |
| Site Handover |  | 20th April 2015 |  |  |
| Contract period | 17/ April/2015 – Jan 16/2016 | 17 April/2015 -– Jan 16/2016 | 16/ April/2015– Jan 15/2016 | 17/ April/2015– Jan 16/2016 |
| Project scope at completion | 270 days/ until Jan 16/2016 | 270 days/until Jan 16/2016 | 270 days/ until Jan 15/2016 | Jan 16/2016 days/ until |
| Completion date according to contract | Data not available | 27/01/2016 | January 26,2016 |  |
| Provisional acceptance | October 29/2016. (19/02/2009) | 17 Sept. 2016, | October 29/2016. (19/02/2009) | October 29/2016. (19/02/2009) |
| Actual completion | Not available | 13/10/2017 | October 31/2016 |  |
| Total number of delays | Not available | 270 calendar days | 279 calendar days | 499 calendar days |
| Number of justified days of delay | Not available | 234 calendar days | 264 calendar days | 479 calendar days |
| Number of unjustified days of delay | Not available | 26 calendar days | 15 calendar days | 20 calendar days |
| Changes of contract duration as compared to the original contract duration | Not available | 86.7 % contract duration extend with justified contract | 97.8 % contract duration extend with justified contract | 177.4% contract duration extend with justified contract |
| Justification of changes | Not available | No need give any more days from justified date | No need give any more days from justified date | No need give any more days from justified date |
| Brief explanation of unjustified changes | Not available | There is no any detail explanation about the unjustified changes. | There is no any detail explanation about the unjustified changes. | There is no any detail explanation about the unjustified changes. |

# Conclusion and Recommendation to the MSG

## Conclusion

As conclusion the following points are noted:

- There is no legal document that shows about change of names of companies such as: Kidane Berihu Building Construction to Kidber Building Construction and Habtamu International Consulting Architects and Engineers PLC to ASPIRE AECOM Architects and Engineer PLC.

- Variations observed  in each contractor is not clearly justified;

- The construction period was delayed by more than 80% as compared with the construction scope.

## Issues Recommended for further review

The further recommendation shall be once discuses with procuring entity and check further unseen document and information in order to forward the final recommendation.

The following table needs brief introductory information/statement

Is it annex?

Table 18.  Disclosure of Procurement Information (for 44 Items)

|  |  | DISCLOSURE OF PROCUREMENT INFORMATION (44 ITEMS) |
| --- | --- | --- |
| Phase | Item of disclosure | Construction | Design | Supervision |
| Procurement information (30 Items) | Date of disclosure | Not available | Not available | Not available |
|  | Contract title | Construction of Dormitory | Planning, Design, Adaptation supervision and contract administration | Design review, supervision and contract administration |
|  | Location | Assosa | Assosa | ssosa |
|  | Procuring entity | Assosa university | Assosa university | Assosa university |
|  | Source for further information | Assosa university project and procurement office | Assosa university project and procurement office | Assosa university project and procurement office |
|  | Date of procurement notice /Invitation date | Selected based on the pervious performance by Addis Ababa Housing construction project | Not Available | For supervision and contract administration (SG consultant) Not available, but for final acceptance contract administration and supervision by Habitamu International consultant, Aug. 6/2016 |
|  | Floating period of the procurement notice | Not Available | Not Available | Not Available |
|  | Media used for procurement notice | Direct selection | Direct selection | Addis Zemen |
|  | Method of procurement | Single sources | Single sources | Competitive |
|  | Type of procurement |  |  |  |
|  | Procurement procedure | Single step | Single step | Two step |
|  | Evaluation criteria | Previous performance | Previous performance | Not available |
|  | Type of contract and project delivery method | Work and Admeasurement | Consultancy services for design lump sum and for supervision and contract administration monthly out put | Consultancy services for design lump sum and for supervision and contract administration monthly out put |
|  | Type and amount of bid security | Unconditional | Unconditional | Unconditional |
|  | Content of any complaint lodged | Not available | Not available | Not available |
|  | Engineer’s estimate | Contractors name | Not available | Not available |
|  |  | United Contractors 19,587,469.02 ETB |  |  |
|  |  | Radar Contractors 25,565,056.99 ETB |  |  |
|  |  | Daniel Contractors 25,565,056.99 ETB |  |  |
|  |  | Kidber Contractors 21,748,910.45 ETB |  |  |
|  | Number of bidders: participated, rejected and declined to submit | Direct selected by Addis Ababa housing construction | Direct selected by ministry of Education based on the pervious performance | Not Available |
|  | Award firm/ contracting firm | United Contractors, Radar Contractors, Daniel Contractors and Kidber Contractors | MH Engineering PLC. Consulting Engineers and Architects | SG consultancy and Habtamu International Consulting Architects and Engineers PLC |
|  | Date of contract award / Acceptance date | Already nominate by Addis Ababa Housing construction | Already nominate by Ministry of Education | Not Available |
|  | Award price/original contract price | United Contractors 19,587,469.02 ETB including VAT 15% | 6,832,955.00 ETB with monthly average supervision fee 99,766.33 for 60 month and For design period 3 month lump sum 846,975.00 ETB including VAT 15% | SG consultant for design review, supervision and contract administration price 2,438,000.00 ETB for 24 months including VAT 15% Habtamu International Consulting Architects and Engineers PLC The total cost for final work supervision 414,460 ETB including VAT 15% |
|  |  | Radar Contractors 25,565,056.99 ETB including VAT 15% |  |  |
|  |  | Daniel Contractors 25,565,056.99 ETB including VAT 15% |  |  |
|  |  | Kidber Contractors 21,748,910.45 ETB including VAT 15% |  |  |
|  | Unit contract price (price /km, price /m2) | Cannot be done | Cannot be done | Cannot be done |
|  | Contract security type and amount | United Contractors, Radar Contractors, Daniel Contractors and Kidber Contractors |  |  |
|  | Date of contract signing |  |  |  |
|  | Contract scope | United Contractors (270 calendar days) Radar Contractors (270 calendar days) Daniel Contractors (270 calendar days), Kidber Contractors (270 calendar days) | 63 months | SG consultant for 24 months Habtamu International Consulting Architects and Engineers PLC until final acceptance done |
|  | Description of contract and contract components | Construction of Dormitory | Planning, Design, Adaptation supervision and contract administration | Design review, supervision and contract administration |
|  | Contract administration entity | Assosa University | Assosa University | Assosa University |
|  | Contract duration | United Contractors 17/ April/2015 – Jan 16/2016 Radar Contractors 17 April/2015 -– Jan 16/2016 Daniel Contractors 16/ April/2015– Jan 15/2016 Kidber Contractors 17/ April/2015– Jan 16/2016 | From March 04/2010- March /2015, in this time only design period has been done | SG Consultant May 08/2015- May 7/2017 Habtamu International Consulting Architects and Engineers PLC, the main contract agreement signed on 21ed of December 2016. |
|  | Contract start / commencement date | Date of sign the agreement at third week of April 2015 Commencing date first week of May 2015 | March 04/2010 | May /2015 |
|  | Intended completion date | Completed |  |  |
| Phase | Item of disclosure | Construction | Design | Supervision |
| Contract implementation (14 items) | Contract status ( ongoing % progress) terminated, completed) | Completed | Completed | The final acceptance On going |
|  | Completion date (revised, projected, actual) | October 31/2016 | Not available | The final acceptance On going by Habtamu International Consulting Architects and Engineers PLC |
|  | Changes to contract duration with reason | Price adjustment and variation work | Contractors did not complete the work | Contractors did not complete the work |
|  | Amount of liquidate damage is applied (penalty for delay) | Not available | Not available | Not available |
|  | Contract price (revised, projected, actual) Changes to contract price with reason | United Contractors changes from 19,587,469.02 to 23,273,967.24 ETB including VAT 15% Reason price adjustment and variation | No change | No Change |
|  |  | Radar Contractors changes from 25,565,056.99 to 29,065,317.84 ETB including VAT 15% Reason price adjustment and variation |  |  |
|  |  | Daniel Contractors change from 25,565,056.99 to 29,790,928.00 ETB including VAT 15% Reason price adjustment and variation |  |  |
|  |  | Kidber Contractors change from 21,748,910.45 to 24,376,637.86 ETB including VAT 15% Reason price adjustment and variation |  |  |
|  | Scope at completion | In average all contractors extended the contract scope by an average 220 days | Not available | Depend on the contractors, the scope extended by 220 days |
|  | Changes to contract scope with reason | Reason price adjustment and variation | Not available | Not available |
|  | Total payment effected | United Contractors 23,273,967.24 ETB including VAT 15% | Not available | Not available |
|  |  | Radar Contractors 29,065,317.84 ETB including VAT 15% |  |  |
|  |  | Daniel Contractors 29,790,928.00 ETB including VAT 15% |  |  |
|  |  | Kidber Contractors 24,376,637.86 ETB including VAT 15% |  |  |
|  | Warranty type and description | Not available | Not available | Not available |
|  | Details of Termination if applied | Not available | Not available | Not available |
|  | Safety measures (accident & death) | Not available | Not available | Not available |
|  | Quality of work (very good, good, inferior, impossible to comment) | Not available | Not available | Not available |
|  | Disputed issues & award details | Not available | Not available | Not available |

Table 19.  Disclosure of Procurement Information (26 Items)

|  | DISCLOSURE OF PROCUREMENT INFORMATION (26 ITEMS) |
| --- | --- |
| Preliminary project information (18 Items) | Date of disclosure | Data not available |
|  | Project owner | Ministry of education |
|  | Project name | Assosa University/ Dormitory |
|  | Sector, sub-sector | Higher education |
|  | Source for further information | Assosa University |
|  | Project Location | Assosa |
|  | Purpose | Expansion of higher education throughout the country, by giving special consideration where previously have no higher education services by near. This is the reflection of political and administrative decentralization and to bring balanced and equitable growth of the economy. |
|  | Project description | Construction of Assosa university phase four dormitory |
|  | Original project scope | Construction of 11 block dormitory |
|  | Project components | Dormitory |
|  | Environmental impact | Data not available |
|  | Land and settlement impact | Data not available |
|  | Estimated budget of the project with breakdown of components | United | Radar | Daniel | Kidane Berihu |
|  |  | Lot 5 – Dormitory ( Do-T2) TV-210 and Do-T2-Tv-211) | Lot 1- Dormitory ( Do-T2-Tv, DO-T4-202 and DO-T2-TV-203 | Lot 4- Dormitory ( DO-T4-Tv-208, Do-T2/Tv-209 and Do-T4-213 | Lot 2 Dormitory ( Do-T4-Tv-200, Do-T4-206 and Do-T2 (miir( -Tv-207) |
|  |  | 19,587,469.02 | 25,565,056.99 | 25,565,056.99 | 21,748,910.45 |
|  | Funding sources | Government of Ethiopia |
|  | Project budget approval date | Not available |
|  | Project start date (planned, actual) | Contractors name | Sign the agreement | Planned date | Actual date |
|  |  | United Building Contractors | 17/ April/2015 | 20 April/2015 | 20 April/2015 |
|  |  | Radar Building Contractors | 17/ April/2015 | 20 April 2015 | 20 April 2015 |
|  |  | Daniel Building Contractors | 16/ April/2015 | 20 April 2015 | 20 April 2015 |
|  |  | Kidane Berihu Building Contractors | 17/ April/2015 | April/2015 | April/2015 |
|  | Planned /Original duration for completing the whole project | Contractors name | Planned /Original |
|  |  | United Building Contractors | 17/ April/2015 – Jan 16/2016 |
|  |  | Radar Building Contractors | 17 April/2015 -– Jan 16/2016 |
|  |  | Daniel Building Contractors | 16/ April/2015– Jan 15/2016 |
|  |  | Kidane Berihu Building Contractors | 17/ April/2015– Jan 16/2016 |
|  |  | United | Radar | Daniel | Kidane Berihu |
|  | Planned /Original cost of the project | 19,587,469.02 including 15%VAT | 25,565,056.99 including 15%VAT | 25,565,056.99 including 15%VAT | 21,748,910.45 including 15%VAT |
| Project information at completion (8 Items) | Cost of the project at completion | 23,273,967.2 | 29,065,317.84 | 29,790,927 | 24,376,637.86 |
|  | Changes of project cost with reason | Price escalation Additional work | Price escalation Additional work | Price escalation Additional work | Price escalation Additional work |
|  | Project completion date (Revised, projected, actual) | Not revised | Not revised | Not revised | Not revised |
|  | Actual duration for completing the whole project | 23,273,967.24 ETB including VAT 15% | 29,065,317.84 ETB including VAT 15% | 29,790,928.00 ETB including VAT 15% | 24,376,637.86 ETB including VAT 15% |
|  | Changes of project duration with reason | Price adjustment ( basic item price increment) and variation( additional work) | Price adjustment ( basic item price increment) and variation( additional work) | Price adjustment ( basic item price increment) and variation( additional work) | Price adjustment ( basic item price increment) and variation( additional work) |
|  | Project scope at completion | 270 days/ until Jan 16/2016 | 270 days/until Jan 16/2016 | 270 days/ until Jan 15/2016 | Jan 16/2016 days/ until |
|  | Changes of project scope with reason | Scope not changed but completion duration change by justified and unjustified delay | Scope not changed but completion duration change by justified and unjustified delay | Scope not changed but completion duration change by justified and unjustified delay | Scope not changed but completion duration change by justified and unjustified delay |
|  | Reference to documents for disclosure upon request (reactive disclosure) | Contract document, payment certificate, Provisional acceptance | Contract document, payment certificate, Provisional acceptance | Contract document, payment certificate, Provisional acceptance | Contract document, payment certificate, Provisional acceptance |
|  | Contract agreement Completion report | Not available | Not available | Not available | Not available |

# Footnotes

Addis Ababa Housing development project sent a letter to Assosa University through reference number ቤ/ግ/ፕ 14/9560 dated on 22 መጋቢት/ 2007 E.C. In the letter all the names of the three contractors are included and their performances are more than 98%. Based on the letter, Assosa University signed agreement with the four contractors (Radar, United, Daniel Tsegaye,  and Kidane Berihu).